## Executive Summary
Topic | Current conclusion | Notes
Scope | Stage 1 through final pilot release | Covers reported Stage 4–6, current bilingualization, and remaining PRD/TRD deliverables.
Immediate priority | Stage 7 — complete Hindi/English coverage | Do not move on until route-by-route coverage and browser verification are evidenced.
Stage 1–3 status | NOT EVIDENCED | The supplied progress log did not establish what was completed in these stages. Recover logs/commits; do not assume complete.
Stage 4–6 status | REPORTED COMPLETE / PARTIAL — VERIFY | Reports include prototype audit, demo safety, nullable values/API path and monitoring integration. Reported outcomes need current repo verification.
Live data status | BLOCKED / NOT DEMONSTRATED | Supabase permission failure was reported; no real source connector end-to-end has been demonstrated.
AI/ML status | NOT IMPLEMENTED AS VALIDATED SYSTEM | No target, ground-truth dataset, baseline comparison, held-out evaluation or independent validation report evidenced.
Production status | NOT VERIFIED | No proof of deployment readiness, server-side RBAC, production notifications, operational runbooks or pilot approval.
Safety gate | MANDATORY | Never present satellite-only estimates as measured groundwater depth; GSS/days-to-crisis stay disabled/experimental until independently validated and approved.
Status definitions | See Status Guide sheet | Reported complete is not the same as independently verified.

## Master Checklist
ID | Stage / Phase | Workstream | Priority | Deliverable / Task | Definition of Done / Acceptance Criteria | Status (evidence-based) | Evidence / Basis | Dependencies / Gate | Next Action
JD-001 | Stage 1 | Requirements, scope and project setup | P0 | Recover and audit the original Stage 1 implementation report and commits | A stage report, commit/hash or repository evidence maps each claimed deliverable to files and tests. | NOT EVIDENCED | Available progress material documents Stage 4 onward; no clear Stage 1–3 completion evidence found in the supplied progress log. | Repository history and prior Antigravity logs | Do not mark this stage complete until evidence is recovered.
JD-002 | Stage 2 | Architecture, data model and foundation | P0 | Recover and audit the original Stage 2 implementation report and commits | A stage report, commit/hash or repository evidence maps each claimed deliverable to files and tests. | NOT EVIDENCED | Available progress material documents Stage 4 onward; no clear Stage 1–3 completion evidence found in the supplied progress log. | Repository history and prior Antigravity logs | Do not mark this stage complete until evidence is recovered.
JD-003 | Stage 3 | Core pages and prototype implementation | P0 | Recover and audit the original Stage 3 implementation report and commits | A stage report, commit/hash or repository evidence maps each claimed deliverable to files and tests. | NOT EVIDENCED | Available progress material documents Stage 4 onward; no clear Stage 1–3 completion evidence found in the supplied progress log. | Repository history and prior Antigravity logs | Do not mark this stage complete until evidence is recovered.
JD-004 | Stage 4 | Prototype audit | P0 | Inventory routes, data sources and current architecture | All routes/components and their actual data dependencies are documented. | REPORTED COMPLETE — VERIFY | Stage 4 audit summary in conversation: 8 pages; pages read local TS fixtures; geospatial API unused by pages at that time. | Repository inspection | Re-run audit against current branch; Stage 4 may be superseded by later changes.
JD-005 | Stage 4 | Prototype audit | P0 | Record baseline build, tests, Git state and security findings | Build/test output, branch/HEAD, dirty files, dependency audit and environment assumptions are recorded. | REPORTED COMPLETE — VERIFY | Reported build passed, 9 unit tests passed, working tree heavily dirty, 2 npm audit findings; Playwright browser install failed. | Current repository state | Capture current git status/log and rerun commands.
JD-006 | Stage 4 | Data safety | P0 | Document Supabase failure and fixture fallback | DB error is visible; fixture fallback is clearly labelled and cannot masquerade as live data. | REPORTED COMPLETE — VERIFY | Audit reported Supabase REST 401 / 42501 and API returning demonstration fixture fallback. | Supabase access review | Retest with current API and browser.
JD-007 | Stage 5 | Scientific claims and demo safety | P0 | Remove unsupported model/calibration claims | No claim of validated GSS, LSTM calibration, CGWB calibration or authoritative crisis estimate without evidence. | REPORTED COMPLETE — VERIFY | Stage 5 report described removal of calibration/LSTM/audit claims and explicit demo labels. | Code review and UI inspection | Search current code and UI for unsupported claims.
JD-008 | Stage 5 | Overview | P1 | Label demo block severity and aggregate KPIs | Demo counts/averages are visibly marked simulated; severity is described as manually classified demonstration data. | REPORTED COMPLETE — VERIFY | Stage 5 report described simulated KPI and severe-block labels; requested exact disclaimer afterward. | Bilingual coverage | Verify exact heading/disclaimer in both languages.
JD-009 | Stage 5 | Monitoring | P1 | Label shared six-point chart as simulated | Chart title, axes, reference line and explanatory text explicitly identify illustrative/demo data. | REPORTED COMPLETE — VERIFY | Stage 5 report said monitoring chart labels shared 6-point series as simulated and reference line illustrative. | Bilingual coverage | Verify charts don't imply block-specific measured history.
JD-010 | Stage 5 | Alerts/interventions | P0 | Prevent demo alerts from being represented as sent | Demo status is visibly simulated; no message is dispatched without approved provider, recipient and review flow. | REPORTED COMPLETE — VERIFY | Stage 5 report described [SIMULATED - NOT SENT] and local role restrictions. | Server-side RBAC; provider approval | Test every alert status and dispatch path.
JD-011 | Stage 5 | Automated tests | P1 | Retain safety regression tests | Safety tests cover unsupported claims, simulated dispatch and null/role behavior and run in CI/local test command. | REPORTED COMPLETE — VERIFY | Stage 5 reported 16/16 tests; later stage reports higher counts. | Current test suite | Run current tests and inspect test coverage.
JD-012 | Stage 6 | Data types and mapping | P0 | Preserve missing indicator values as null | Missing source values remain null end-to-end; no silent zero substitution; UI shows No Data/N/A. | REPORTED COMPLETE — VERIFY | Stage 6 report lists nullable EnvironmentalIndicators, mapper updates, demoPolicy mean filtering and UI null handling. | Current code review | Test each indicator and aggregation edge case.
JD-013 | Stage 6 | Geospatial API | P0 | Add source-aware geospatial blocks API | API returns source, demo flag, count, fetchedAt and safe error; failure mode is explicit. | REPORTED COMPLETE — VERIFY | Stage 6 report describes /api/geospatial/blocks response contract and fixture fallback. | Supabase access | Test live success, empty result, timeout, permission error and fallback.
JD-014 | Stage 6 | Monitoring | P0 | Connect Monitoring page to API | Monitoring fetches service data and visibly differentiates live DB, fixture and unavailable states. | REPORTED COMPLETE — VERIFY | Stage 6 report says monitoring page fetches API and shows source/error notice. | Bilingual coverage | Verify all source-state labels translate.
JD-015 | Stage 6 | Database access | P0 | Diagnose Supabase 42501 permission denied | Root cause is proven with least-privilege review; fix is tested without exposing sensitive tables. | BLOCKED | Stage 6 report says remote request still fails 401 / 42501 for administrative_units. | DB owner review and explicit approval | Inspect remote grants/RLS; do not apply migration blindly.
JD-016 | Stage 6 | Database migration | P0 | Review pending public read grants migration | Each grant is justified; RLS is reviewed; sensitive/PII tables remain restricted; remote change explicitly approved. | BLOCKED | Local migration reportedly grants SELECT on four public tables; not applied remotely. | C06 permission diagnosis | Request approval before any remote permission change.
JD-017 | Stage 6 | Tests/build | P1 | Verify nullable data and API tests | Current test suite and production build pass from current working tree; results captured. | REPORTED COMPLETE — VERIFY | Stage 6 report claimed 17/17 tests and build pass. | Current repository | Re-run tests/build and save raw output.
JD-018 | Stage 7 (current) | Bilingualization | P0 | Complete Hindi/English coverage audit across all routes | Route/component inventory identifies every user-facing string and missing translation in both languages. | IN PROGRESS / NOT FULLY VERIFIED | Language report lists context/dictionary and five integrated pages; Map Explorer not listed. | Current code and browser | Run read-only audit first; no unrelated features.
JD-019 | Stage 7 (current) | Bilingualization | P0 | Verify global language switch and persistence | Hindi default, English toggle, persistence after navigation/refresh, no broken page state. | REPORTED COMPLETE — VERIFY | Report says LanguageContext, localStorage key jaldrishti_language_v1 and toggle were added. | Browser verification | Test fresh session, route changes, refresh and both languages.
JD-020 | Stage 7 (current) | Bilingualization | P0 | Translate Map Explorer and all dynamic map UI | Layers, legends, filters, markers, popups, block details, errors and caveats all translate. | NOT EVIDENCED / LIKELY GAP | Latest language report did not list Map Explorer among integrated pages. | Language dictionary/context | Add Map Explorer to translation coverage matrix.
JD-021 | Stage 7 (current) | Bilingualization | P0 | Translate chart axes, statuses, form validation, empty/error/loading states | No important hardcoded interface text remains; dynamic status labels use translation keys. | IN PROGRESS / VERIFY | Report claims centralized dictionary but no exhaustive route matrix or browser evidence supplied. | All routes | Search hardcoded strings; add missing keys and tests.
JD-022 | Stage 7 (current) | Bilingualization | P1 | Test Hindi rendering and responsive layout | No clipping/overflow; readable Hindi; controls and caveats usable on desktop and mobile. | NOT EVIDENCED | No browser verification results in latest language report. | Bilingual pages complete | Run route-by-route browser checks in both languages.
JD-023 | Stage 7 (current) | Bilingualization | P1 | Add translation completeness regression tests | Automated tests fail for missing keys and untranslated required UI labels; both languages render. | REPORTED COMPLETE — VERIFY | Language report claimed 18/18 tests and build pass, but not full coverage proof. | Current test suite | Inspect test assertions and add route-level coverage.
JD-024 | Stage 8 | Map Explorer & UX | P0 | Verify Map Explorer initial load | Map, markers and legend appear without clicking a layer; valid bounds and loading/error states work. | VERIFY | Prior user report said map initially blank until layer click; fix execution not evidenced. | Stage 7 bilingualization for final acceptance | Reproduce in fresh browser and fix root cause.
JD-025 | Stage 8 | Map Explorer & UX | P1 | Verify map layer switching | Each layer updates data/legend and returning to default restores expected markers. | VERIFY | No conclusive post-fix browser report. | Stage 7 bilingualization for final acceptance | Test every layer and reset.
JD-026 | Stage 8 | Map Explorer & UX | P1 | Simplify technical wording and reduce warning clutter | Plain-language labels with one concise demo notice; essential scientific caveats remain clear. | IN PROGRESS / VERIFY | Prompt was provided; execution and route-wide verification not evidenced. | Stage 7 bilingualization for final acceptance | Check actual UI against prompt.
JD-027 | Stage 8 | Map Explorer & UX | P1 | Verify filters and block detail | Filters return correct blocks and detail content is consistent with source and language. | NOT EVIDENCED | No end-to-end evidence supplied. | Stage 7 bilingualization for final acceptance | Test no results, one result and reset.
JD-028 | Stage 9 | Live data & ingestion | P0 | Confirm pilot geography and official boundaries | Approved district/block list, stable IDs, geometry source/version, CRS and owner documented. | NOT STARTED / DECISION NEEDED | PRD/TRD say exact districts/blocks pending approval. | Supabase permission review and approved source access | Obtain pilot-owner approval before seeding data.
JD-029 | Stage 9 | Live data & ingestion | P0 | Inventory CGWB/state groundwater observations | Coverage, historical period, well locations, units, cadence, quality flags, license/access path and gaps documented. | NOT STARTED / NOT EVIDENCED | No actual connector or validated data access evidenced. | Supabase permission review and approved source access | Prove one source can be accessed lawfully.
JD-030 | Stage 9 | Live data & ingestion | P0 | Inventory approved rainfall and EO products | Specific product, resolution, time cadence, QA flags, access terms, latency and usage limits documented. | NOT STARTED / NOT EVIDENCED | IMD/GEE/satellite connectors not demonstrated. | Supabase permission review and approved source access | Select products only after source-access check.
JD-031 | Stage 9 | Live data & ingestion | P0 | Implement one real source end-to-end | Real source record flows through ingestion, validation, storage/API, UI and provenance; reproducible test snapshot retained. | NOT STARTED | Current source path is DB/fixture; no real ingestion demonstrated. | Supabase permission review and approved source access | Start with accessible, permitted CGWB observation data if feasible.
JD-032 | Stage 9 | Live data & ingestion | P0 | Build data quality and freshness monitoring | Duplicates, impossible values, stale data, CRS errors, missingness and schema drift are detected and visible. | NOT STARTED | PRD/TRD require quality controls; implementation evidence absent. | Supabase permission review and approved source access | Implement source-specific contracts and QA.
JD-033 | Stage 9 | Live data & ingestion | P0 | Remove fixtures from live claims | Fixtures remain demo-only; no production UI labels them live; fallback source is obvious and tested. | IN PROGRESS / VERIFY | Explicit fixture labeling reported, but page coverage is not proven. | Supabase permission review and approved source access | Audit all pages and API consumers.
JD-034 | Stage 9 | Live data & ingestion | P0 | Verify time-series charts use actual selected block data | Correct block-specific observations, dates, units and gaps; no shared sample series presented as real. | NOT STARTED / VERIFY | Stage 5 said same six-point chart used across blocks and labelled simulated. | Supabase permission review and approved source access | Replace only after real series available.
JD-035 | Stage 10 | Science & AI/ML | P0 | Define scientifically measurable target and forecast horizon | Science owner approves target definition, geographic scale, horizon and operational use. | NOT STARTED / DECISION NEEDED | PRD/TRD list target as open question; GSS and days-to-crisis are candidates only. | Stage 9 real historical data | Do not train until target is defined.
JD-036 | Stage 10 | Science & AI/ML | P0 | Create historical ground-truth dataset | Timestamped independent observations with location, units, QA and sufficient temporal/spatial coverage. | BLOCKED BY DATA | No verified training/validation dataset reported. | Stage 9 real historical data | Assess data sufficiency and licensing.
JD-037 | Stage 10 | Science & AI/ML | P0 | Create baseline and leakage-safe evaluation | Time-based and geographic holdouts; comparison to persistence/statistical baseline; reproducible metrics. | NOT STARTED | No model evaluation report supplied. | Stage 9 real historical data | Plan before model selection.
JD-038 | Stage 10 | Science & AI/ML | P0 | Train candidate model only if justified | Reproducible pipeline, model version, feature lineage, missing-data behavior and repeatable inference. | NOT STARTED | No trained/validated model evidenced. | Stage 9 real historical data | Prefer simplest model that passes baseline.
JD-039 | Stage 10 | Science & AI/ML | P0 | Validate calibration, uncertainty and errors independently | Independent review of false positives/negatives, calibration, uncertainty and generalization limits. | NOT STARTED | PRD/TRD require independent validation. | Stage 9 real historical data | Science gate before user-facing prediction.
JD-040 | Stage 10 | Science & AI/ML | P0 | Keep GSS and days-to-crisis disabled/unverified | No authoritative output until target, ground truth, uncertainty and governance approval pass. | GUARDRAIL REQUIRED | PRD/TRD explicitly defer these claims until validation. | Stage 9 real historical data | Retain demo/experimental labels or remove from operational UI.
JD-041 | Stage 10 | Science & AI/ML | P0 | Run shadow-mode pilot | Candidate signals reviewed without public dispatch; false-alert burden and reviewer workload measured. | NOT STARTED | TRD defines shadow mode as a later gate. | Stage 9 real historical data | Requires validated pipeline and pilot owner.
JD-042 | Stage 11 | Governance, security & operations | P0 | Enforce authentication and server-side RBAC | API enforces user identity and role/scope on reads/writes/exports; negative tests deny unauthorized access. | NOT VERIFIED | Stage 5 role restrictions described as UI/demoPolicy; server-side enforcement not proven. | Depends on relevant data/science implementation | Inspect middleware, API handlers and RLS.
JD-043 | Stage 11 | Governance, security & operations | P0 | Create versioned official scheme catalogue | Each action has official source, effective date, applicability, eligibility caveat and reviewer/owner. | NOT STARTED / NOT EVIDENCED | PRD/TRD say hard-coded scheme mapping must be replaced/verified. | Depends on relevant data/science implementation | Do not present scheme names as approved eligibility.
JD-044 | Stage 11 | Governance, security & operations | P0 | Implement human-reviewed alert lifecycle | Candidate → review → approval → dispatch; audit trail, dedupe, recipient authorization and kill switch. | NOT STARTED / NOT EVIDENCED | Demo alert statuses exist; production workflow not proven. | Depends on relevant data/science implementation | Keep demo dispatch disabled.
JD-045 | Stage 11 | Governance, security & operations | P0 | Messaging sandbox integration | Test recipients only; provider acceptance, delivery and acknowledgement are distinct; retries idempotent. | NOT STARTED | No provider integration demonstrated. | Depends on relevant data/science implementation | Choose provider and approve templates/privacy.
JD-046 | Stage 11 | Governance, security & operations | P0 | Security/dependency review | Current dependency audit triaged; secrets protected; no sensitive data exposed; threat model addressed. | IN PROGRESS / VERIFY | Earlier audit reported two npm findings; current state unknown. | Depends on relevant data/science implementation | Re-run npm audit and review remediation.
JD-047 | Stage 11 | Governance, security & operations | P0 | Accessibility and low-bandwidth checks | Keyboard/accessibility labels, color-independent statuses, mobile/low bandwidth behavior tested. | NOT STARTED / NOT EVIDENCED | PRD/TRD specify localization and low-connectivity testing. | Depends on relevant data/science implementation | Add manual and automated checks.
JD-048 | Stage 11 | Governance, security & operations | P0 | Deployment and operations runbook | Environment configuration, secret rotation, health checks, backup/restore, rollback, incident owner and costs documented. | NOT STARTED / NOT EVIDENCED | No verified deployment or ops acceptance supplied. | Depends on relevant data/science implementation | Do not claim production-ready.
JD-049 | Stage 11 | Governance, security & operations | P0 | Pilot go/no-go review | Data access, science, security, language comprehension, alert workflow, costs and ownership approved. | NOT STARTED | PRD/TRD release gates; exact pilot units and owners pending. | Depends on relevant data/science implementation | Schedule review only after prior gates.
JD-050 | Stage 12 | Release acceptance | P0 | Run complete route-by-route regression suite | Every route tested in Hindi and English with demo/live/error/missing-data states. | NOT STARTED | Only aggregate unit-test claims supplied; full route-level evidence absent. | All previous applicable gates | Execute after bilingual and data work.
JD-051 | Stage 12 | Release acceptance | P0 | Verify build, tests, lint and security audit | Commands pass or known failures are documented and assigned; raw outputs saved. | REPORTED PASS — RE-RUN | Latest reports claimed 18 tests/build pass; lint previously skipped and audit findings remained. | All previous applicable gates | Capture fresh evidence from current branch.
JD-052 | Stage 12 | Release acceptance | P0 | Prepare pilot acceptance pack | Architecture, source inventory, test report, language coverage, security review, model card if applicable, runbooks and limitations compiled. | NOT STARTED | Required by PRD/TRD acceptance logic; not evidenced. | All previous applicable gates | Compile after release gates pass.
JD-053 | Stage 12 | Release acceptance | P0 | Controlled pilot release and monitoring | Named pilot units and users; human review; rollback; support owner; measured success metrics. | NOT STARTED | No verified production deployment or pilot authorization. | All previous applicable gates | Only after formal go/no-go.

## Status Guide
Status | Meaning | How to use
VERIFIED COMPLETE | Evidence directly inspected or test result reproduced in current state. | Can be closed once evidence link/hash/date is recorded.
REPORTED COMPLETE — VERIFY | Progress report says complete, but current implementation or test has not been independently checked. | Keep open until acceptance criteria are re-tested.
IN PROGRESS | Partially implemented or incomplete coverage. | List remaining work and owner.
BLOCKED | A dependency, approval, access or decision prevents safe progress. | Resolve dependency; do not bypass approval.
NOT STARTED | No implementation evidence supplied. | Plan and assign.
NOT EVIDENCED | Available files/logs do not establish status; not necessarily unbuilt. | Recover stage logs, commits or inspect repository.
GUARDRAIL REQUIRED | Must remain disabled or restricted until release gate passes. | Do not mark as a missing feature to rush into production.